## DailySprintPlanning
Daily sprint
Nummer | Datum | Tijd | Les | Opmerkingen
1 | 2017-02-20 | 10:15 | Database
2 | 2017-02-21 | 10:15 | Web
3 | 2017-02-22 | 10:15 | Web
4 | 2017-02-23 | - | - | Studiedag
5 | 2017-02-24 | 10:30 | Pauze

## PB
Product Backlog
Remaining effort after sprint
User Story |  | Details | Prio | Value | Init effort | 1 | 2 | 3 | 4 | 5 | 6
Als een.. | Wil ik..
Gebruiker | kunnen inloggen |  | 1 | 10 | 2
Leerling | mijn voortgang bewaren |  | 1 | 10 | 3
Docent | lesonderwerpen kunnen aanmaken/wijzigen/verwijderen |  | 1 | 9 | 3
Docent | lessen kunnen aanmaken/wijzigen/wijzigen |  | 1 | 9 | 3
Docent | leerlingen/docenten toevoegen/bewerken/verwijderen |  | 1 | 9 | 3
Ontwikkelaar | Testrapport ontwikkelen |  | 1 | 8 | 1
Leerling | ingeplande lessen kunnen maken |  | 2 | 10 | 1
Leerling | ingeplande toetsen kunnen maken |  | 2 | 10 | 1
Leerling | resultaat terug krijgen aan het einde van een les/toets |  | 2 | 9 | 2
Leerling | cijferlijst kunnen inzien |  | 3 | 5 | 2
Docent | rapportage inzien tekstueel |  | 3 | 5 | 2
Docent | lessen/toetsen inplannen per student |  | 3 | 7 | 3
Docent | rapportage inzien grafisch |  | 4 | 1 | 5

## SP1
Sprint 1 Backlog
Remaining effort after day
User Story | Sprint Task | Teamlid | Init effort | 1 | 2 | 3 | 4 | 5 | 6
As a buyer I want to place a book in a shopping cart | Modify database | Joan | 5 | Remaining effort after day 1: 3; Remaining effort after day 2: 2; Remaining effort after day 3: 0
| Create webpage UI | Jeroen | 11 | Remaining effort after day 1: 7; Remaining effort after day 2: 5; Remaining effort after day 3: 5
| Create webpage (Javascript logic) | Lambert | 12 | Remaining effort after day 1: 12; Remaining effort after day 2: 8; Remaining effort after day 3: 6
| Automated acceptance tests | Erik | 9 | Remaining effort after day 1: 4; Remaining effort after day 2: 2; Remaining effort after day 3: 2
| Update buyer help webpage | Lambert | 1 | bar: Remaining effort after day 1 to Remaining effort after day 3
As a buyer I want to remove a book from a shopping cart | Merge PHP code | Jeroen | 2 | Remaining effort after day 1: 2; Remaining effort after day 2: 0; Remaining effort after day 3: 0
| Complete layer level test | Lambert | 5 | Remaining effort after day 1: 4; Remaining effort after day 2: 3; Remaining effort after day 3: 2
| Change reader http API | Erik | 8 | Remaining effort after day 1: 8; Remaining effort after day 2: 8; Remaining effort after day 3: 6